## Slide 1
OER Africa
OER Africa: Participatory Action Research Grant (PAR)
Open University of Tanzania
June 2015

## Slide 2: OER Africa PAR Grant - Aim
Through the following activities and outputs, OER Africa will seek to build collaboratively an evidence base for precise ways in which OER processes can contribute to better understanding:
    (a) the transformation of higher education teaching and learning practices, and
    (b) what policy, regulatory, systemic, and cultural barriers exist to implementing these processes and how they can be overcome.

## Slide 3: OUT – Collaborative Activities
  Policies:
  Review and updating of OUT institutional policies, including OER/IP and ICT/eLearning.
  Digital Fluency Course for Academics:
  All five modules - completed design, development and mounting on the OUT Moodle server
  Quality review process and revision for all 5 modules
  Pilot delivery of all five modules at OUT and selected Tanzanian higher education institutions
  Module evaluations and further revision, if required
  Publishing of all five modules of the course as open courseware on a variety of OER repositories including the ACDE open course repository.
  Identified OUT courses mounted on appropriate OER repositories:
  Establishment of a publishing framework and process for open courses at OUT
  Establish institutional OER publishing team, roles and institutional stakeholders
  Institutional capacity built with respect to:
      Searching for and using/adapting OERs
      Licensing and copyright clearance
      Publishing to a selected repository
      Quality assurance processes for release of OUT OER

## Slide 4: OUT (1.1)
Output 1: A Deepened Understanding of How OER Practices Can Support Sustained Transformation of Teaching and Learning in African Universities.
Goal 1: Institutionalize OER practices in ways that support effective pedagogical transformation
  Systematic review of relevant OUT policies initiated
      OER Institutional Analysis Workshop – November 2014
        Current status of OER at OUT established
      OER Experience Sharing workshop – January 2015
        12 draft resolutions generated
        approved by the Library Board in mid-February 2015
      MOU ready for signature June 2015
Notes:       Notes:
        Contact from Liz Levey, Open Access expert consultant – possible guidance?

## Slide 5: OUT (1.2)
Output 1: A Deepened Understanding re OER in support of T&L.
Goal 2: Develop capacity of university staff re OER for pedagogical transformation:
  Digital Fluency Course – all 5 modules completed and pilots initiated
      Status of institutional course code/ host Faculty: ODF 001
      Mod 2 being piloted – open for ACDE member viewing
      Quality improvement underway
Notes:     QI an ongoing process

## Slide 6: OUT (2.1)
Output 2: Accumulated understanding of how OER practices and policy can support transformation of teaching and learning in African universities is widely shared and is incorporated into advocacy.
Goal 1: Action Research and Advocacy
  Documentation / dissemination of lessons learned (e.g. Case Studies, Research Articles, Stories / Anecdotes)
      Prof. Nihuka liaison for the research agenda.
      Research Summary compiled and regularly updated

## Slide 7
This work is licensed under a Creative Commons Attribution 4.0 License
Thank you
Catherine Ngugi
OER Africa Project Director
catherine.ngugi@oerafrica.org
Brenda Mallinson
Learning Technologies Consultant
brendam@saide.org.za